## Sheet1
	Bi-Weekly Meetings to review data, methodology, and drafts	Revised-Updated edited chapters 1-3 to advisor	Chapter 4 edited final draft to advisor	Chapter 5 edited final draft to advisor	Dissertation final draft to advisor for final round of comments	Dissertation draft to committee	Defense rehearsal	TARGET: Dissertation defense	Post-defense Revision	Submission to Graduate Studies
Plan of Record	01 Feb - 22 May 2023	01 May 2023	08 May 2023	31 August 2023	14 September 2023	28 September 2023	12 October 2023	26 October 2023	09 November 2023	12 November 2023

Potentially Accelerated Plan	01 Feb - 09 May 2023	01 May 2023	08 May 2023	22 May 2023	29 May 2023	05 June 2023	30 May 2023	06 June 2023	13 June 2023	16 June 2023

#	Task				Amount Completed	Effort (days)	Start date	Completion date
1	Roll up cash flow statements into a single spreadsheet				2/3	4	22 March 2023	26 March 2023
2	(a) Record bond data from years 2008-2022 in Data Dashboard. / (b) Add debt summaries				15/15 / 11/11	4	26 March 2023	30 March 2023
3	Cross-reference Form 990 with financial statements for years 2008-2022				Does not yield useful information.	0	30 March 2023	30 March 2023
4	Review Related Party Transactions for years 2008-2022 / SB740 Grants: 2012-13 - 2021-22 / Land & facilities leases: 2022 only				Done	3	30 March 2023	02 April 2023
5	Find and record all bond prospectuses.				4/10	2	02 April 2023	04 April 2023
6	Cross-reference years 2008-2022 of board meeting data with financial statements.					4	04 April 2023	08 April 2023
7	Research and characterize types of bonds: conduit bonds, NMTC, loans, forgiven loans				80%	1	08 April 2023	09 April 2023
8	Research and then cross-reference venture funds with financial statements					4	09 April 2023	13 April 2023
9	Review & incorporate relevant data from StopRocketship, EduResearcher, & ScoopIt, and HBS & GBS case studies					3	13 April 2023	16 April 2023
10	Record in Data Dashboard grants and donations.				100%	1	16 April 2023	17 April 2023
11	Review and cross-reference petitions and renewals with financial statements.					4	17 April 2023	21 April 2023
12	Review and cross-reference leases with financial statements.					3	21 April 2023	24 April 2023
11	Submit Chapters 1- 3 draft					7	24 April 2023	01 May 2023
12	Submit Chapter 4 draft					7	01 May 2023	08 May 2023
13	Submit Chapter 5 draft					14	08 May 2023	22 May 2023
14	Dissertation final to advisor					7	22 May 2023	29 May 2023
15	Submit dissertation to committee					7	29 May 2023	05 June 2023
16	Defense rehearsal					7	05 June 2023	12 June 2023
17	Defend!					7	12 June 2023	19 June 2023
18	Post-defense revision					7	19 June 2023	26 June 2023
19	Submit dissertation to Graduate Studies					4	26 June 2023	30 June 2023
Notes
1	Dates in bold are meetings with Roxana