## Sheet1
	Bi-Weekly Meetings to review data, methodology, and drafts		Revised-Updated edited chapters 1-3 to advisor	Chapter 4 edited final draft to advisor	Chapter 5 edited final draft to advisor	Dissertation final draft to advisor for final round of comments	Dissertation draft to committee	Defense rehearsal	TARGET: Dissertation defense	Post-defense Revision	Submission to Graduate Studies
Plan of Record	01 Feb - 22 May 2023		17 March 2023	05 May 2023	31 August 2023	14 September 2023	28 September 2023	12 October 2023	26 October 2023	09 November 2023	12 November 2023

Potentially Accelerated Plan	01 Feb - 09 May 2023	01 Feb 2023	27 March 2023	24 April 2023	09 May 2023	16 May 2023	23 May 2023	30 May 2023	06 June 2023	13 June 2023	16 June 2023

#	Task				Effort (days)	Start date	Completion date
0.9	Roll up cash flow statements into a single spreadsheet				4	17 February 2023	21 February 2023
1	Record bond data from years 2014-2022 in Data Dashboard.				4	21 February 2023	25 February 2023
2	Cross-reference Form 990 with financial statements for 15 years.				1	25 February 2023	26 February 2023
3	Find and record all bond prospectuses.				4	26 February 2023	02 March 2023
4	Cross-reference 15 years of board meeting data with financial statements.				7	02 March 2023	09 March 2023
5	Research and characterize types of bonds: conduit bonds, NMTC, loans, forgiven loans				1	09 March 2023	10 March 2023
6	Research and then cross-reference venture funds with financial statements; include their Form 990s.				4	10 March 2023	14 March 2023
	Review & incorporate relevant data from StopRocketship, EduResearcher, & ScoopIt.				3	14 March 2023	17 March 2023
7	Record in Data Dashboard grants and donations.				1	17 March 2023	18 March 2023
8	Review and cross-reference petitions and renewals with financial statements.				4	18 March 2023	22 March 2023
9	Review and cross-reference leases with financial statements.				1	22 March 2023	23 March 2023
	Quality time with my son				7	23 March 2023	30 March 2023
		End of data collection & organizing / Start of writing
10	Submit Chapters 1- 3 draft				4	30 March 2023	03 April 2023
11	Submit Chapter 4 draft				21	03 April 2023	24 April 2023
12	Submit Chapter 5 draft				15	24 April 2023	09 May 2023
13	Dissertation final to advisor				7	09 May 2023	16 May 2023
14	Submit dissertation to committee				7	16 May 2023	23 May 2023
15	Defense rehearsal				7	23 May 2023	30 May 2023
16	Defend!				7	30 May 2023	06 June 2023
17	Post-defense revision				7	06 June 2023	13 June 2023
18	Submit dissertation to Graduate Studies				3	13 June 2023	16 June 2023
Notes
1	Graduate school deadline is second Monday in November.
2	All dates are "No later than 11;59pm".
3	Dates in bold are fixed. The others are relative to a fixed date .